## Sheet1
YEAR -2 |  |  | DATE | WHO | NOTES
| October | Agree Date for Tea Dance | 2017-10-03 | Committee | 2019-01-20
|  | Book Hall | 2017-10-03 | Celia
|  | Update RSCDS Dance Diary | 2017-10-03 | Suzanne
|  | Book musicians | 2017-10-03 | Celia
YEAR -1
| February | Update Website with Date
| April | Finalise Dance programme
Send copy to musicians as confirmation
| May | Update Website with Programme and crib
| May | Produce Ad |  |  | Remember to change the rehearsal stuff
| June | Submit Ad to Reel
| September | Agree who will do raffle
Agree who will do flowers
Devise plan for ticket sales
Print fliers and tickets
Agree complimentary tickets
Distribute tickets and spreadsheet to ticket sellers
| Oct - December | Implement plan, Monitor sales
Gather raffle prizes
Buy raffle books
YEAR 0
| January | Check time rooms are availabilty at M Hall
| Week-2 | Obtain contact no for caretaker
Instruct caretaker on no of tables, easel etc
Update email (RSCDS)
Unroll direction signs
Check supplies
| Week-1 | Agree who is bringing what:
Tea,coffee, milk, squash from stores, fruit tea
Plastic cups, napkins, paper plates
Banqueting roll as tablecloth
Runners & tablecloths
Flowers
Raffle
Jugs
Sellotape, Scissors, Blutack,Pins
Washing -up liquid
Teatowels
Float
Payment for musicians /caretaker tip
Thank-you presents
Masterlist of tickets/attendees
| February | Review tea dance and update checklist accordingly